## Setup Sequence
Sage Intacct Setup Instructions — Meridian Fabrication Group ('Project Ignite')
For: Implementation Partner / Configuration Consultant ¦ Prepared by: Marcus Chen, Controller, MFG
This is the master build sequence. Complete phases in order — each phase depends on the one before it (e.g., dimensions must exist before the Chart of Accounts references them; the COA must exist before opening balances load). Each phase links to a dedicated file/folder listed in the 'Reference File' column.
Phase | Task | Detail / Instructions | Reference File | Owner | Target Date
1 | Create company & entities | Create top-level company 'Meridian Fabrication Group LLC' and subsidiary entity 'Meridian Precision Components LLC'. Set fiscal calendar to standard 12-period calendar year (Jan–Dec). Base currency USD. | 01-Company-Entity-Setup/Company-and-Entity-Setup.xlsx | Implementor | Week 1
2 | Configure elimination entity | Create consolidation/elimination entity 'MFG-Consolidated-Elim' for automated intercompany elimination on consolidated reporting. | 01-Company-Entity-Setup/Company-and-Entity-Setup.xlsx | Implementor | Week 1
3 | Build dimension structures | Create Location, Department, Customer Type, and Item Class dimension lists before building the Chart of Accounts (accounts reference these dimensions). | 02-Dimensions/Dimensions-Import.xlsx | Implementor | Week 1
4 | Import Chart of Accounts | Import the redesigned COA, including new WIP, Intercompany Payable, and job-cost-related accounts. Tag each account with required dimension structure. | 03-Chart-of-Accounts/Chart-of-Accounts-Import.xlsx | Implementor | Week 2
5 | Create users & assign roles | Create all 35 named users, assign to the appropriate permission role, and set module access per the Role-Based Permissions Matrix. | 04-Users-Roles-Permissions/Users-Roles-Permissions-Import.xlsx | Implementor | Week 2
6 | Import Customer master | Import all 180 active customer records including billing address, terms, and assigned sales rep. | 05-Customers-Vendors-Items/Customers-Import.xlsx | Implementor | Week 3
7 | Import Vendor master | Import all 340 active vendor records (post-dedup), including 1099 eligibility flag. | 05-Customers-Vendors-Items/Vendors-Import.xlsx | Implementor | Week 3
8 | Import Item master | Import all 95 active items with Item Class dimension assignment and unit of measure. | 05-Customers-Vendors-Items/Items-Import.xlsx | Implementor | Week 3
9 | Import active Projects/Jobs | Import all 241 active jobs with budget by phase and cost type (Labor, Material, Overhead, Subcontract, Freight). | 06-Projects-Jobs/Projects-Jobs-Import.xlsx | Implementor | Week 4
10 | Configure approval workflows | Build tiered AP approval workflow ($0–4,999 auto / $5,000–24,999 Dept Manager / $25,000+ CFO) and PO approval threshold ($2,500+ Ops Manager). | 08-Approval-Workflows/Approval-Workflows-Setup.xlsx | Implementor | Week 4
11 | Configure integrations | Build Salesforce (Closed Won → Sales Order) and ADP Workforce Now (bi-weekly payroll GL feed) integrations. Test in sandbox first. | 09-Integrations-Setup/Integrations-Setup-Instructions.xlsx | Implementor + Lena Ford (IT) | Week 5
12 | Load opening trial balance | Load opening GL trial balance as of cutover date for both entities. Must net to zero and tie to legacy trial balance. | 07-Opening-Balances/Opening-Trial-Balance-Import.xlsx | Implementor | Week 6 (post-UAT)
13 | Load open AP bills | Load all open/unpaid vendor bills as of cutover date. | 07-Opening-Balances/Open-AP-Bills-Import.xlsx | Implementor | Week 6 (post-UAT)
14 | Load open AR invoices | Load all open/unpaid customer invoices as of cutover date. | 07-Opening-Balances/Open-AR-Invoices-Import.xlsx | Implementor | Week 6 (post-UAT)
15 | Validate & reconcile | Reconcile every loaded dataset against legacy control totals (trial balance, AP aging, AR aging, job budgets). No variance should remain open. | See: 06-Data-Migration-Validation/Validation-Report.md (Project Ignite Portfolio) | Marcus Chen + Implementor | Week 6
16 | UAT & sign-off | Run UAT test cases; obtain formal sign-off before production cutover. | See: 07-UAT/ (Project Ignite Portfolio) | Marcus Chen | Week 7-8
17 | Go-live cutover | Freeze legacy system, final data load, activate integrations, provision users, open system. | See: 09-Cutover/ (Project Ignite Portfolio) | Implementor + Marcus Chen | Cutover weekend